## Slide 1
Key Challenges Operational failures highlighted deficiencies in the maintenance organization and processes Labor issues complicated the relationship with maintenance staff Management wanted to consider outsourcing the jet engine maintenance in order to definitively resolve the problems | Why BSI was Selected Consultant identified a major impending operational problem before it occurred Outside support helpful due to a politically charged situation
Project Scope All aircraft and engine types in the fleet Preventive maintenance Unplanned repairs Heavy overhauls and light maintenance Global operations 5-point program Reorganization Process optimization Variability reduction Outsourcing Vendor management | Project Approach Articulated key business processes Applied a decision tree flowchart to decide which processes should be retained based on strategic and operational criticality Designed and implemented kitting templates Compared the current situation with an optimized scenario and an outsourcing scenario Prepared a tender to outsource the function in part and/or in whole Sent the bid to market, evaluated and chose a vendor Developed vendor management integration and evaluation processes
Financial Benefits Realized $3 million annual savings $2 million per year reduction in labor costs | Operational Benefits Realized 20% reduction in lead time Risk offloading to suppliers Simplified labor relations
ABOUT THE CLIENT | 
Industry | Logistics
Revenues | $35 billion
Employees | 100,000
Location | United States
BSI Service or Solution | Outsourcing
Outsourcing Evaluation, Planning, and Implementation
CASE
STUDY 19